## Procurement Process
Lebanon Procurement Flows
Phase | CA User Dept | CA Minister | CTB | Checking Factor | Deliverable Produced
1
plans from all CAs
Advanced Planning Notice
2
draft tender dossier
|  |  |  | notices are logged | tender notice
tenders received
3
evaluation report & award recommendation
contract
award notice
4
Departmental Procurement Plan
CA Procurement Plan
Consolidated Govt Proc Plan on PPMA website
consolidated Govt Proc Plan
raises requisition
prepares specification
tender dossier
check for compliance
return comments
revise dossier
publish notice
Phase 1
Planning & Organization
Phase 2
Requisition & Advertising
Issues ITB
receives tenders
Phase 4
contract
management
allows minimum or greater period
Phase 3
Tender Operations
Contract Award
opens tenders
evaluates compliance
technical
financial
evaluation report & recommendation
signs contract
award notice

## Planning
Lebanon Procurement Planning Process
| CA User Dept | CA Minister | CTB | Minsitry of Finance | Prime Minister | Parliament | Timetable | Deliverable Produced
[7 empty] | December | interim plans from Cas
Interim Annual Plan
[7 empty] | January | Interim Planning Notice
Approved budget
by 15 March
[7 empty] | by 15 April | Final Annual Procurement Plan
4 months before tender
[7 empty] | 3 months before tender | draft tender dossier
Drafts Departmental Procurement Plan + Staff Requirements
Consolidates plan & budget for CA
Consolidated Interim Govt Proc Plan on PPMA website, National Gazette, newspapers
consolidates Govt Proc Plan
submits final procurement plan
consolidates final plans
publish final annual plan on PPMA website, National Gazette, newspapers
consolidates Govt budget proposals
presents budget proposals
approves item by item
amends budgets
revises plans
prepares specification
tender dossier
4 months before due date

## Committee Members
لجان المشتريات في إدارة المناقصات
المرحلة | قسم المشتريات والصفقات في الجهة المتعاقدة | الوزير في الجهة المتعاقدة | إدارة الصفقات العمومية | عامل التحقق | النواتج/المنجزات
1
تلقّي إجابات كافة الجهات المتعاقدة
2
|  |  |  | تأكيد المشاركة في لجنة المشتريات | لجنة المشتريات
3
|  |  |  | اجتماع أعضاء لجنة المشتريات | محضر فض العروض
التقييم والتوصيات
يقدّم لائحة بالأعضاء المحتملين
يحيل اسماء مرشّحي الوزارات
المرحلة الأولى: الترشيح
المرحلة الثانية: الاختيار
يجمّع لوائح أسماء المرشّحين
اختيار أعضاء لجنة المشتريات الفردية
4 اسابيع قبل قبل الموعد النهائي
يجيز المشاركة
إرسال اعضاء لجنة المشتريات
إرسال الخبراء
تقديم خدمات الأمانة
المرحلة الثالثة: فض العروض والتقييم
في اليوم المخصص لفض العروض

## Technical Specifications
Technical Specifications
Is there a
 Lebanese standard
 Lebanese specification
 International Standard?
is reference to it precluded by a legal duty, eg on health & safety or security grounds
do you choose to use another standard?
you must not indicate a trademark, patent, type or specific origin unless this is essential and qualified by "or equivalent"
use, in order of preference,
 standard having currency in the region
 another Lebanese technical approval
 any other standard
and be prepared to consider products manufactured to a different design but having equivalent performance
you must refer to the Lebanese standard implementing the International Standard or Lebanese specification
yes
yes
yes
no
no
no

## Dossier+Notice
Check of Tender Dossier and Publication of Tender Notice
| CA User Dept | CTB | CTB DG | Weeks before Contract Start | Deliverable Produced | Order | Action | Weeks | Weeks before Contract Start
[6 empty] | 11 | Contractor delivers/ starts work | 3 | 0
[6 empty] | 10 | Contract signed | 1 | 3
[6 empty] | 9 | Evaluation & Recommendation | 1 | 4
|  |  |  | 16 |  | 8 | Bid opening | 3 | 5
[6 empty] | 7 | Gazette publishes notice | 2 | 7
[6 empty] | 6 | PPMA send notice to Gazette | 0.25 | 9
[6 empty] | 5 | PPMA fix bid opening date | 0.25 | 9
|  |  |  | 12 |  | 4 | CA revises TD | 1 | 10
|  |  |  | 11 |  | 3 | PPMA reviews & comments | 1 | 11
[6 empty] | 2 | CA sends TD to PPMA | 1 | 12
[6 empty] | 1 | CA User Dept drafts TD | 4 | 16
10
9
9
7
5
4
3
0
Drafts Tender Dossier
selects PC secretariat
check document
prepares & sends notice for publication
revises dossier & resubmits
issue envelopes to bidders
puts dossier on website
prepares opening record & checklist

## Evaluation+Award
Opening, Evaluation, Recommendation and Contract Signing
| Procurement Committee | Secretariat | Bidders | CTB DG | Checking Factor | Deliverable Produced
opens bids
records bids
attend (optional)
approves evaluation report
sends recommendation to CA Minister for signing
preliminary evaluation
technical evaluation
agree shortlist
opens financial envelopes
financial evaluation
submit evaluation report
records actions
records bids
get technical expert(s)
records actions
draft evaluation report
answer questions
depart
attend (optional)